## OFFICE MOVE CHECKLIST
OFFICE MOVE CHECKLIST
STAGE ONE: The Foundations
Task | Deadline | Owner | Budget | Checkbox
Appoint your office move project manager and project team
Review your current lease and establish any early-break costs
Set out your criteria and conduct necessary staff surveys
Research costs and set your budget
Establish your office move deadline
Research office removal companies and office moving insurance costs
Start searching online for office spaces that suit your business needs
Document your plan and timeline
Shortlist, discuss and choose your new office and complete necessary paperwork
STAGE TWO: Communicate
Task | Deadline | Owner | Budget | Checkbox
Ensure your current client lists are up to date
Run a detailed audit of all online and offline and list content requiring and update to the address
Notify the post office of your new address
Collaborate with your legal teams to update necessary contracts with the new address
Update your social media and online accounts (including Google Business etc.) with the new address
Review lists of partners and stakeholders to inform of change of address (update lists where necessary)
Run an audit on stationery and branding material to update addresses where necessary
Review and update all delivery subscriptions
Communicate your plans to your staff (let them know how/if they can get involved)
Give notice to current landlord/building manager
Set a date in the diary for staff to update the address in email signatures
Book your chosen office removals company
Start coordinating your office move logistics with your IT team to discuss IT systems and equipment needs
Send change of address notices to clients, customers, partners, industry bodies and media publications of which you are a member or subscriber
Inform your internet service providers of your office move and discuss internet connection needs
Inform your telecoms provider of your office move and arrange for any necessary updates to your phone number, phone systems or cabling needs
STAGE THREE: Logistics
Task | Deadline | Owner | Budget | Checkbox
Conduct an audit of your current office furniture and identify any new furniture you may need
Map out your new office design with a detailed floor plan and dimensions
Plan out your new space according to office space and desk blocks
Identify meeting room spaces and communal spaces in the new office layout
Arrange for any external temporary storage where required
Plan for any stationery and equipment for the new office
Establish any security needs for the new office
Arrange/appoint cleaning services (both for checking out of the old office and regular cleaning for the new space)
Check out and book loading bays or dedicated parking for moving day
Finalise all new contract paperwork
Discuss and make arrangements for any new IT equipment for the new office space and meeting rooms
Check-in with internet / telecoms and other necessary providers to ensure the big day runs smoothly and without excessive downtime